## Slide 1: PETRA-IV
What is planned and how things are progressing
Rüdiger Onken – DESY - MHF
Trieste, November, 2023

## Slide 2: Agenda
PETRA IV (overview)
The rf system
The rf- components used
Installing & first operating experience with prototype system
The timeline

## Slide 3: DESY site in Hamburg
History of PETRA (Positronen-Elektronen-Tandem Ring Anlage)
Ring accelerator for electrons and positrons; later pre-accelerator for HERA for protons & positrons
Length: 2304 meters
Commissioning: 1978
1978-1986: particle physics
1987-2007: pre-accelerator for HERA and source for X-rays
Since 2010: one of the brightest storage ring X-ray sources in the world
23 beamlines with almost 60 measuring stations

## Slide 4: Future plan: PETRA-IV (overview)
Parameter | Brightness mode | Timing mode
Beam energy | 6 GeV | 6 GeV
Bunch current | 0.125 mA | 1 mA
Beam current | 200 mA | 80 mA
No. bunches | 1600 | 80
H Emittance | < 20 pm | < 40 pm
V Emittance | 2-10 pm | 5-20 pm
Bunch length (rms) | < 40 ps | < 70 ps
Rel. energy spread | < 1.e-3 | < 1.4e-3
Lifetime (Touschek + Vacuum) | > 10 h | > 5 h
Energy loss: 4 MeV/turn
Revolution frequency: 130.121 kHz
1 mA bunch current ≙ 7.7 nC
Bunch length w/o 3rd harmonic system = 23 ps
Clear the tunnel & build a new machine, using ¾ of the old tunnel
Many new buildings e.g. rf building and another experimental hall (1/4 of the ring length)
Plenty of work on all the infrastructure (old and in need of renovation)

## Slide 5: Let’s focus on the rf-system

## Slide 6: RF-System design
Fundamental (500 MHz): Sum-voltage 8 MV
24 single-cell-cavity, HOM-damped (BESSY-type)
24 SSA, output power 120 kW cw
Harmonic (1.5 GHz): Sum-voltage 2.3 MV
24 single-cell-cavity, either HOM-damped (scaled BESSY-type) or Shintake
24 SSA, output power 10 kW
4 fundamental-subsystems and 4 harmonic-sub-systems grouped together as one rf-system. The PETRA IV rf has 6 rf-systems (4*500 MHz + 4*1.5 GHz)
Power- and water-supplies should be as independent as possible. The timing and the controls are also separate (avoidance of single point of failure)
LLRF is realized in µTCA-technique, control of water and temperatures is done by PLC
One of six RF-systems

## Slide 7: PETRA-IV overview
RF-building, hosting all the rf-systems
New rf-building
As close to the tunnel as possible
Should be compact so that it fits between the infrastructure currently still in use
Building should be ready before the shut-down
Hosting:
  24 pc 500 MHz SSA & HOM-damped cavities
  24 pc 1.5 GHz SSA & HOM-damped cavities
  Reference-distribution
  2nd floor, Magnet power supplies, Water, climatization, diagnostics …

## Slide 8: Why so much??

## Slide 9: RF-System design
Best compromise:
Trip compensation with not too many components involved
Trip of one sub-system should not cause a beam loss
If one sub-system fails, the other components are not excessively stressed
Control and regulation for a quartet are manageable
Shutdown of one system (=4 sub-systems) should be possible
Detail, one rf-System = two Quartets of SSA & cavities
6 rf-systems in total
Grouping / clustering – 6 RF-systems

## Slide 10: Redundancy & Trip-compensation
The rf should not have the “ERROR pole position”

Sub-system : power: 56.4 kW
Uc: 333 kV
≙ 1.1 MV/m
Sub-system : power: 82.8 kW
Uc: 444 kV
≙ 1.5 MV/m


Sub-system : power: 71.9 kW
Uc: 400 kV
≙ 1.3 MV/m
Sub-system : power: 101.7 kW
Uc: 533 kV
≙ 1.8 MV/m
Normal operating
∑ Uc: 8 MV  1.33 MV/system
One system is off
∑ Uc: 8 MV  1.6 MV/system
Concept:
Smooth shut-down of one system should be possible
Slow response to slow failures (shutdown of the subsystem in case e.g. of overtemperature in the cavity)
Arcs or vacuum events
  blank out rf
  3 remaining sub-systems take over
  Necessity of voltage compensation has to be developed and proofed
Critical:
Tuning of either fundamental and 3rd harmonic systems – to the beam and to each other
in normal operation
in error case
in transition between both cases

## Slide 11: The rf- components used

## Slide 12: Components of the rf systems
Fundamental system, 500 MHz:
SSA: 120 kW
HOM-damped cavities: BESSY-type (Modified to re-use refurbished DESY IPC & DESY Plunger)
One site, in test, as prototype-system

## Slide 13: Components of the rf systems
Refurbishing of plunger (without contact springs):
In house (DESY)
• Reusing main parts of existing plungers
• Design without the problem zone -"contact springs”
• Another flange for better inspection of the plunger bottom
Will be tested in Prototype HOM-damped cavity @ PETRA-III
Larger plunger diameter (compared to other institutes) makes tuning a bit more fragile
  Micro stepping
Reprocessing of the input-couplers:
Already in progress
Treatment of vacuum inner surfaces (copper surfaces and ceramics / etching and sandblasting)
Conditioning @ coupler test stand up to > 200 kWcw
Reusing some components
Einkopplerbild

## Slide 14: Components of the rf systems
3rd harmonic system, 1.5 GHz:
Active
SSA: 15 kW
Scaled (BESSY-type) HOM-damped Cavity
Under test @ BESSY
  Collaboration (ALBA, HZB & DESY)

## Slide 15: The booster rf system
SSA: 120 kW
  It will be ramped (5 Hz or temporarily cw @ flat-top)
  Energy buffer will be necessary
5 cell cavity
  9 pc in stock
  Need to be cleaned

## Slide 16: First operating experience

## Slide 17: Installing & first operating experience with prototype system
1rst half 2022:
  Preparation of SSA-hutch,
  installation of water infrastructure,
  mounting circulator and waveguides in the hutch and waveguide to tunnel
Summer SD 2022:
  Preparation of the insertion area
    new vacuum system
    preparation of the girder for the cavity
Fall 2022
  Cavity conditioning @ test stand (CaTs)
  Took 600 h up to 560 kV (but should be much faster)
Winter SD 2022:
  Installation of HOM-damped cavity in the tunnel
1rst half 2023:
  Passive operation of HOM-damped Cavity during test runs
May 2023:
  SSA delivered and installed on site
Summer SD 2023:
  Connecting SSA and cavity
  Conditioning of cavity
July 2023:
  First active operation on the beam Up to now about 50 days
Sine then:
  Eliminate childhood issues of the SSA
  Integration of the system into the DOOCS control system
  Adapting the µTCA hardware and software to the needs of a ring accelerator
  Elaboration of
    beamloading compensation,
    transient beamloading compensation,
    Feedback (direct feedback)

## Slide 18: The timeline

## Slide 19: Time-line (may be floating ?)
Preliminary status, as of September 2022
Start procurement Jun. 2024
  All rf-parts should be delivered within 3 Years
Planning & construction of rf-building Jan. 2025 – Jul. 2026
P-III Shutdown Jan. 2027
P-IV Commissioning Aug. 2028

## Slide 20
Rüdiger Onken / Peter Hülsmann
WP 2.12 – RF-systems
ruediger.onken@desy.de / peter.huelsmann@desy.de
+49 40 8998 3453 / +49 40 8998 2782
Thank you

## Slide 21: PETRA-IV overview, beamlines
Phase-I Beamlines (existing Halls)
16 x BLs
+ HIKA
PXW Beamlines (new hall – Phase-II)
12 x BLs
+ 2 DBLs
All fully new
Day 1

## Slide 22: Trumpf SSA Characterization